## Sheet1
Requested Date | Due Date | Received or Completed | Item/Action - see promotion training manual available through Office of Faculty Affairs for more information
2013-02-01 | 2013-02-15 | 2013-02-15 | List of promotion and/or tenure candidates from chair or departmental PAT Committee
2016-02-08 |  |  | If there is a joint department or school notify them of promotion to ensure receipt of joint review and ballot
2013-02-15 | 2014-02-28 |  | Send email to candidates requesting following items:
List of 6 extramural reviewers
CV in School of Medicine format with latest revision date in upper right hand corner
Personal statement (required)
5 most significant journal articles during period of review submitted electronicaly in ONE pdf file to beth.williams@louisville.edu
Copies of acceptance letters for any articles in-press or accepted on CV
Summative Peer Teaching Evaluation
Reviews by recipients of the service, if applicable
Prepare promotion binder: Place Promotion/Tenure Triptych Information sheet in clear front pocket and last name in spine of the binder; Insert promotion checklistand Log Sheet for Promotion/Tenure in front of binder; prepare names for tabs: Forms, Intramural, Extramural, etc
Obtain Awards Summary from University Reports UBM-13A with assistance of GR-02 Grant Proposals/Award by EMPLID
Obtain teaching evaluations from student/resident coordinators and consolidate into 1-2 page summary
Gather annual work plans and annual merit reviews for each year of the review period
List of extramural evaluators finalized by chair and candidate
Prepare letters to extramural evaluators and make copies of materials to be included with letter -see promotion process instructions
Chair letter and additional materials are sent to extramural evaluators -see promotion process for enclosures
Schedule departmental PAT Committee for a date that will allow enough time for the return of extramural letters
Prepare Memorandum #1-3
Send Memorandum #1 to candidate after extramural evaluations are received and before departmental PAT meets. Identity of extramural reviewers should be redacted (hiden) from promotion candidate before binder is examined.
Prepare departmental PAT meeting agenda and ballots for attendees
Send materials to departmental PAT Committee at least 48 hrs prior to meeting. Provide the criteria to the committee
Departmental PAT Committee meets and votes
Obtain ballots from all eligible and ineligble executive faculty
Tally faculty votes for promotion and record on Ballot-Departmental Approval Form. If tenure applies, record tenure votes on separate ballot.
Send Memorandum #2 to candidate after departmental PAT Committee has met. Candidate has opportunty to add materials for reconsideration by the Departmental Committee.
Departmental PAT Committee provides Memorandum #3- Validitiy Statement along with evaluation.
Prepare P103 and P102. P103 requires chair's signature and P102 requires faculty's signature
Draft chair's letter to dean using promotion and/or tenure template that fits the candidate's area of excellence, rank and track (term or tenure track). Provide the chair with the departmental PAT evaluation and letters of support from reviewers.
Candidate completes the Departmental Assurance Form in binder
| 2013-08-01 |  | Deliver original binder to Office of Faculty Affairs, keep copy for departmental files.
Updated 7/8/16